## Data
Initiative/Project | Teams | Phase | Capacity Allocation Estimate | # of Sprints Estimate | Start Date | End Date | Type | Status | Notes | Jira | Theme | Business Objective
PCG Non-Del Core Notifications | SFMC | Planning and Design |  |  | 2026-02-01 | 2026-02-28 | Enhancement | Done |  | CDM-26827 | Fulfillment & Operations Excellence | To modernize the P3 loan communication framework by centralizing transactional messaging within Salesforce Marketing Cloud (SFMC). This initiative eliminates dependency on inflexible legacy systems, ensures data integrity through direct real-time queries, and empowers the business with full control over the branding and delivery logic of critical loan status updates.
PCG Non-Del Core Notifications | SFMC | Implementation and Delivery | 30% | 3 | 2026-03-01 | 2026-04-15 | Enhancement | In Progress |  | CDM-26827 | Fulfillment & Operations Excellence | To modernize the P3 loan communication framework by centralizing transactional messaging within Salesforce Marketing Cloud (SFMC). This initiative eliminates dependency on inflexible legacy systems, ensures data integrity through direct real-time queries, and empowers the business with full control over the branding and delivery logic of critical loan status updates.
NLVA (AI Virtual Agent) | CRM CDL | Planning and Design |  |  | 2026-01-01 | 2026-02-15 | Strategic Initiative | Done |  | PBTI-206 | AI & Intelligent Automation | To revolutionize PennyMac’s customer service framework by replacing traditional IVR systems with advanced Natural Language Virtual Agents (NLVA). By integrating AI-driven NLU and NLG capabilities, this project aims to eliminate call misrouting, unlock business capacity through automated initial outreach, and provide a seamless, human-like interaction experience for both inbound inquiries and outbound campaigns.
NLVA (AI Virtual Agent) | CRM CDL | Implementation and Delivery | 20% | 3 | 2026-02-15 | 2026-05-15 | Strategic Initiative | In Progress |  | PBTI-206 | AI & Intelligent Automation | To revolutionize PennyMac’s customer service framework by replacing traditional IVR systems with advanced Natural Language Virtual Agents (NLVA). By integrating AI-driven NLU and NLG capabilities, this project aims to eliminate call misrouting, unlock business capacity through automated initial outreach, and provide a seamless, human-like interaction experience for both inbound inquiries and outbound campaigns.
TPO Horizon Migration | CRM TPO, SFMC | Planning and Design |  |  | 2026-03-01 | 2026-04-30 | Strategic Initiative | Backlog |  |  | Platform Modernization & Legacy Sunset | To transition the Broker Lending channel from its legacy Loan Origination System (LOS) to a modern, cloud-native platform. This migration aims to streamline the end-to-end loan lifecycle, enhance system performance, and provide a more intuitive interface for internal users and external partners, mirroring successful modernization efforts across other business units.
TPO Horizon Migration | CRM TPO, SFMC | Implementation and Delivery | 50% | 16 | 2026-05-01 | 2026-11-30 | Strategic Initiative | Backlog |  |  | Platform Modernization & Legacy Sunset | To transition the Broker Lending channel from its legacy Loan Origination System (LOS) to a modern, cloud-native platform. This migration aims to streamline the end-to-end loan lifecycle, enhance system performance, and provide a more intuitive interface for internal users and external partners, mirroring successful modernization efforts across other business units.
Customer Preference Management (CPM) | CRM CDL, SFMC | Implementation and Delivery | 50% | 4 | 2026-01-01 | 2026-04-15 | Strategic Initiative | In Progress |  |  | Marketing Technology & Operations | To implement a centralized, compliant platform that allows customers to fine-tune their communication preferences by specific marketing program types (e.g., Rate Alerts, General Marketing) and channels. By giving customers the choice to "opt-down" rather than completely out, Pennymac aims to preserve marketing opportunities, improve the customer experience, and ensure strict adherence to data privacy regulations.
CDP Personalization in CRM | CRM CDL | Planning and Design |  |  | 2026-01-01 | 2026-01-15 | Strategic Initiative | Backlog |  |  | AI & Intelligent Automation | To enhance Sales productivity and speed-to-lead by integrating the Customer Data Platform (CDP) with Leadforce CRM. This initiative shifts Credco trigger alerts from daily to hourly delivery, empowering Loan Officers to prioritize high-intent opportunities faster while utilizing real-time behavioral attributes for highly personalized script delivery and borrower interactions.
CDP Personalization in CRM | CRM CDL | Implementation and Delivery | 20% | 2 | 2026-02-15 | 2026-03-15 | Strategic Initiative | Backlog |  |  | AI & Intelligent Automation | To enhance Sales productivity and speed-to-lead by integrating the Customer Data Platform (CDP) with Leadforce CRM. This initiative shifts Credco trigger alerts from daily to hourly delivery, empowering Loan Officers to prioritize high-intent opportunities faster while utilizing real-time behavioral attributes for highly personalized script delivery and borrower interactions.
TPO Contact Center | CRM TPO | Planning and Design |  |  | 2026-01-01 | 2026-01-15 | Strategic Initiative | Done |  |  | Strategic Growth & Channel Support | To implement a fully integrated software solution for the TPO Account Executive (AE) Call Center, leveraging Salesforce as the primary CRM, Five9 for telephony, and an AI-powered assistant to enhance AE productivity, streamline workflows, and improve data tracking for performance management.
TPO Contact Center | CRM TPO | Implementation and Delivery | 50% | 2 | 2026-01-15 | 2026-02-15 | Strategic Initiative | In Progress |  |  | Strategic Growth & Channel Support | To implement a fully integrated software solution for the TPO Account Executive (AE) Call Center, leveraging Salesforce as the primary CRM, Five9 for telephony, and an AI-powered assistant to enhance AE productivity, streamline workflows, and improve data tracking for performance management.
Horizon - Rapid Refi | CRM CDL | Planning and Design |  |  | 2026-01-01 | 2026-01-15 | Strategic Initiative | Done |  |  | Fulfillment & Operations Excellence | To bridge the gap between self-service applications and sales follow-up by automating lead generation from the consumer portal into the CRM. This ensures that every Rapid Refinance application is captured, assigned to a Loan Officer in real-time, and prioritized for engagement, thereby reducing drop-off rates and optimizing the sales funnel.
Horizon - Rapid Refi | CRM CDL | Implementation and Delivery | 20% | 1 | 2026-02-01 | 2026-02-15 | Strategic Initiative | Done |  |  | Fulfillment & Operations Excellence | To bridge the gap between self-service applications and sales follow-up by automating lead generation from the consumer portal into the CRM. This ensures that every Rapid Refinance application is captured, assigned to a Loan Officer in real-time, and prioritized for engagement, thereby reducing drop-off rates and optimizing the sales funnel.
Horizon - Self-Serve Scheduling | SFMC | Planning and Design |  |  | 2026-01-01 | 2026-01-15 | Strategic Initiative | Done |  |  | Omnichannel Engagement | To empower borrowers with a self-service closing scheduler accessible via digital communications. By enabling customers to select closing dates that automatically sync back to the Horizon LOS, this initiative improves the borrower experience while significantly reducing the manual coordination and follow-up workload for MST agents.
Horizon - Self-Serve Scheduling | SFMC | Implementation and Delivery | 30% | 2 | 2026-01-15 | 2026-02-15 | Strategic Initiative | Done |  |  | Omnichannel Engagement | To empower borrowers with a self-service closing scheduler accessible via digital communications. By enabling customers to select closing dates that automatically sync back to the Horizon LOS, this initiative improves the borrower experience while significantly reducing the manual coordination and follow-up workload for MST agents.
Horizon - MFD Enhancements | Zendesk | Implementation and Delivery | 50% | 10 | 2026-01-01 | 2026-10-15 | Enhancement | In Progress |  |  | Fulfillment & Operations Excellence | To transform the fulfillment experience by expanding Zendesk’s functional capabilities for MFD Agents supporting borrowers through the fulfillment process. By integrating Zendesk directly with the Horizon LOS, agents can manage end-to-end fulfillment steps within a single interface, eliminating "swivel-chair" workflows and ensuring borrowers receive seamless, proactive support from loan submission through to funding.
Attack Surface Management | CRM CDL, CRM TPO, SFMC, Zendesk | Implementation and Delivery | 10% | 20 | 2026-01-01 | 2026-12-31 | Maintenance | In Progress |  |  | InfoSec, Risk & Compliance | To strengthen Pennymac’s cybersecurity posture by implementing a systematic process for remediating Attack Surface Management (ASM) findings. This initiative empowers division owners to proactively reconcile vulnerabilities—including End-of-Life systems, misconfigurations, and web-based threats (XSS, Injection)—ensuring continuous patching and protection against zero-day exploits while safeguarding sensitive data.
PDM - Servicing | CRM CDL, SFMC, Zendesk | Planning and Design |  |  | 2026-01-01 | 2026-01-31 | Strategic Initiative | Backlog |  |  | Enterprise Data Strategy | To implement the Pennymac Data Model (PDM) as the enterprise-wide standard for all downstream data consumption originating from the new servicing platform. By aligning servicing data with the universal PDM schema, this initiative ensures data consistency across business units, simplifies reporting and analytics, and accelerates the integration of servicing data with other core enterprise systems.
PDM - Servicing | CRM CDL, SFMC, Zendesk | Implementation and Delivery | 20% | 3 |  |  | Strategic Initiative | Backlog |  |  | Enterprise Data Strategy | To implement the Pennymac Data Model (PDM) as the enterprise-wide standard for all downstream data consumption originating from the new servicing platform. By aligning servicing data with the universal PDM schema, this initiative ensures data consistency across business units, simplifies reporting and analytics, and accelerates the integration of servicing data with other core enterprise systems.
PDM for TPO Horizon | CRM TPO, SFMC | Planning and Design |  |  | 2026-03-15 | 2026-05-15 | Strategic Initiative | Backlog |  |  | Enterprise Data Strategy | To design, model, and implement the PDM data standard for the TPO production channel as it migrates to the new Loan Origination System (LOS). By creating a single, governed source of truth that publishes updates in PDM format, this initiative enables standardized downstream consumption across all integrated systems and facilitates the decommissioning of legacy data interfaces.
PDM for TPO Horizon | CRM TPO, SFMC | Implementation and Delivery | 20% | 3 | 2026-05-15 | 2026-11-15 | Strategic Initiative | Backlog |  |  | Enterprise Data Strategy | To design, model, and implement the PDM data standard for the TPO production channel as it migrates to the new Loan Origination System (LOS). By creating a single, governed source of truth that publishes updates in PDM format, this initiative enables standardized downstream consumption across all integrated systems and facilitates the decommissioning of legacy data interfaces.
CDL Legacy Sunset | SFMC, CRM CDL, Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Strategic Initiative | Backlog |  |  | Platform Modernization & Legacy Sunset | To formally decommission and sunset the legacy Loan Origination System (LOS) and its supporting infrastructure following the successful migration to the modern production platform. This initiative includes the retirement of legacy integrations and the archival of historical data, ultimately reducing operational overhead, eliminating technical debt, and mitigating risks associated with maintaining outdated systems.
CDL Legacy Sunset | SFMC, CRM CDL, Zendesk | Implementation and Delivery | 10% | 1 |  |  | Strategic Initiative | Backlog |  |  | Platform Modernization & Legacy Sunset | To formally decommission and sunset the legacy Loan Origination System (LOS) and its supporting infrastructure following the successful migration to the modern production platform. This initiative includes the retirement of legacy integrations and the archival of historical data, ultimately reducing operational overhead, eliminating technical debt, and mitigating risks associated with maintaining outdated systems.
FTC Data Disposal | CRM CDL, SFMC, Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Strategic Initiative | Backlog |  |  | InfoSec, Risk & Compliance | To establish a comprehensive enterprise-wide framework for the secure disposal of Non-Public Personal Information (NPPI) in accordance with the FTC Safeguard Rule. This initiative involves the systematic identification, archival, and deletion or anonymization of inactive customer data across internal applications, vendor platforms, and decommissioned systems to ensure federal compliance and protect consumer privacy.
FTC Data Disposal | CRM CDL, SFMC, Zendesk | Implementation and Delivery | 10% | 1 |  |  | Strategic Initiative | Backlog |  |  | InfoSec, Risk & Compliance | To establish a comprehensive enterprise-wide framework for the secure disposal of Non-Public Personal Information (NPPI) in accordance with the FTC Safeguard Rule. This initiative involves the systematic identification, archival, and deletion or anonymization of inactive customer data across internal applications, vendor platforms, and decommissioned systems to ensure federal compliance and protect consumer privacy.
Communication Platform Power+ Chat Strategy | Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Strategic Initiative | Backlog | After Feb26 design session, do not anticipate any work for Zendesk. |  | Omnichannel Engagement | To modernize communication within the TPO channel by migrating Client Management, Closing, and Underwriting teams to the Five9 platform. This initiative integrates omni-channel capabilities (Voice, SMS, Chat) directly into the Power+ and Settlement Agent portals via a "Help+ wizard," replacing inefficient email-based workflows with real-time collaboration and intelligent routing to ensure brokers and partners are connected to the right specialists instantly.
Communication Platform Power+ Chat Strategy | Zendesk | Implementation and Delivery |  |  |  |  | Strategic Initiative | Backlog |  |  | Omnichannel Engagement | To modernize communication within the TPO channel by migrating Client Management, Closing, and Underwriting teams to the Five9 platform. This initiative integrates omni-channel capabilities (Voice, SMS, Chat) directly into the Power+ and Settlement Agent portals via a "Help+ wizard," replacing inefficient email-based workflows with real-time collaboration and intelligent routing to ensure brokers and partners are connected to the right specialists instantly.
Salesforce as Client System of Record | CRM TPO | Planning and Design |  |  | 2026-03-01 | 2026-04-01 | Strategic Initiative | In Progress |  |  | Platform Modernization & Legacy Sunset | To transition client/partner administrative data and the end-to-end approval lifecycle to a centralized CRM platform as the primary System of Record (SOR). This initiative unifies sales, service, and onboarding interactions into a single 360-degree view, enforcing data validation and automated synchronization with the Loan Origination System (LOS) and other downstream systems. By automating the push of approved profiles and metadata, the organization ensures a single version of truth, improves data quality, and eliminates manual entry and redundant workflows across the enterprise.
Salesforce as Client System of Record | CRM TPO | Implementation and Delivery | 50% | 3 |  |  | Strategic Initiative | Backlog |  |  | Platform Modernization & Legacy Sunset | To transition client/partner administrative data and the end-to-end approval lifecycle to a centralized CRM platform as the primary System of Record (SOR). This initiative unifies sales, service, and onboarding interactions into a single 360-degree view, enforcing data validation and automated synchronization with the Loan Origination System (LOS) and other downstream systems. By automating the push of approved profiles and metadata, the organization ensures a single version of truth, improves data quality, and eliminates manual entry and redundant workflows across the enterprise.
Sub-servicing Client Request Management Tool | Zendesk | Planning and Design |  |  | 2026-03-01 | 2026-04-01 | Enhancement | In Progress |  | CDM-28785 | Strategic Growth & Channel Support | To modernize the subservicing client support framework by replacing manual tracking processes with an integrated, automated request management system. This initiative leverages a scalable support platform to centralize ticket submissions via the client portal, implement intelligent routing and SLA tracking, and provide real-time status visibility for both internal teams and subservicing clients, ensuring the operational capacity required for significant portfolio growth.
Sub-servicing Client Request Management Tool | Zendesk | Implementation and Delivery | 50% | 3 |  |  | Enhancement | Backlog |  | CDM-28785 | Strategic Growth & Channel Support | To modernize the subservicing client support framework by replacing manual tracking processes with an integrated, automated request management system. This initiative leverages a scalable support platform to centralize ticket submissions via the client portal, implement intelligent routing and SLA tracking, and provide real-time status visibility for both internal teams and subservicing clients, ensuring the operational capacity required for significant portfolio growth.
Post-Closing Items Tracking | Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | In Progress |  |  | Fulfillment & Operations Excellence | To modernize the management of post-closing tasks by implementing a structured workflow environment for TPO and CDL production. By moving from manual spreadsheets to a categorized system—covering Collateral, Servicing Updates, and Production Support—this initiative enables automated SLA tracking and robust reporting, ensuring timely remediation of loan-level items and strict adherence to regulatory compliance standards.
Post-Closing Items Tracking | Zendesk | Implementation and Delivery | 50% | 3 |  |  | Enhancement | Backlog |  |  | Fulfillment & Operations Excellence | To modernize the management of post-closing tasks by implementing a structured workflow environment for TPO and CDL production. By moving from manual spreadsheets to a categorized system—covering Collateral, Servicing Updates, and Production Support—this initiative enables automated SLA tracking and robust reporting, ensuring timely remediation of loan-level items and strict adherence to regulatory compliance standards.
Kirby Deprecation and Replacement | CRM CDL, SFMC | Implementation and Delivery | 20% | 1 | 2026-03-13 | 2026-03-13 | Maintenance | In Progress |  |  | Enterprise Data Strategy | To modernize the data ecosystem by deprecating the legacy Kirby ingestion tool in favor of robust, scalable data landing infrastructure for the CET team. This initiative creates standardized ingestion patterns that eliminate technical dependencies, improve pipeline reliability, and introduce advanced functionality to accelerate data delivery for critical business operations.
SFMC Pipeline Deployment Automation | SFMC | Implementation and Delivery | 20% | 1 | 2026-03-13 | 2026-03-13 | Maintenance | Backlog |  |  | Marketing Technology & Operations | To implement a robust CI/CD pipeline for Salesforce Marketing Cloud (SFMC) by selecting and integrating a specialized deployment automation tool. This initiative aims to replace high-risk manual deployment processes with automated version control and migration workflows, significantly reducing environment inconsistencies, minimizing release-related errors, and accelerating the delivery of marketing campaigns and transactional communications.
Service Order | Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | In Progress |  |  | Fulfillment & Operations Excellence | To enhance operational efficiency for the Service Orders team by migrating workflow management from a shared email inbox to a dedicated Zendesk group. This initiative enables the structured labeling and prioritization of diverse task types—including appraisal/AVM delivery, flood certifications, fraud alerts, and dispositions—providing visibility into volumes and ensuring faster, more accurate processing of critical loan-level service orders.
Service Order | Zendesk | Implementation and Delivery | 50% | 2 |  |  | Enhancement | Backlog |  |  | Fulfillment & Operations Excellence | To enhance operational efficiency for the Service Orders team by migrating workflow management from a shared email inbox to a dedicated Zendesk group. This initiative enables the structured labeling and prioritization of diverse task types—including appraisal/AVM delivery, flood certifications, fraud alerts, and dispositions—providing visibility into volumes and ensuring faster, more accurate processing of critical loan-level service orders.
Scowtt | CRM CDL | Planning and Design |  |  | 2026-03-01 | 2026-03-15 | Enhancement | In Progress |  |  | AI & Intelligent Automation | To establish a secure and automated data integration between the CRM (LeadForce) and the Scowtt predictive modeling platform. This initiative involves mapping core CRM objects, configuring secure access through Field-Level Security (FLS), and ensuring a robust data sync to support AI-driven propensity scoring, ultimately empowering the marketing team with high-accuracy pilot data for targeted customer engagement.
Scowtt | CRM CDL | Implementation and Delivery | 20% | 1 | 2026-03-15 | 2026-04-01 | Enhancement | Backlog |  |  | AI & Intelligent Automation | To establish a secure and automated data integration between the CRM (LeadForce) and the Scowtt predictive modeling platform. This initiative involves mapping core CRM objects, configuring secure access through Field-Level Security (FLS), and ensuring a robust data sync to support AI-driven propensity scoring, ultimately empowering the marketing team with high-accuracy pilot data for targeted customer engagement.
Acquia Digital Asset Management | SFMC | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | In Progress |  |  | Marketing Technology & Operations | To implement an enterprise-grade Digital Asset Management (DAM) solution integrated with the marketing communication platform. This initiative centralizes all digital assets—images, videos, and templates—providing a single source of truth for marketing teams. By automating asset availability within the delivery tools, the organization reduces manual upload times, ensures global brand consistency, and improves speed-to-market for multi-channel campaigns.
Acquia Digital Asset Management | SFMC | Implementation and Delivery | 10% | 1 |  |  | Enhancement | Backlog |  |  | Marketing Technology & Operations | To implement an enterprise-grade Digital Asset Management (DAM) solution integrated with the marketing communication platform. This initiative centralizes all digital assets—images, videos, and templates—providing a single source of truth for marketing teams. By automating asset availability within the delivery tools, the organization reduces manual upload times, ensures global brand consistency, and improves speed-to-market for multi-channel campaigns.
CDL Salesforce MFD Workflow (Zendesk Migration) | CRM CDL, Zendesk | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | In Progress |  |  | Fulfillment & Operations Excellence | To provide a unified fulfillment environment for the Mortgage Success Team (MST) by migrating all core workflows from Zendesk to the enterprise CRM (LeadForce). This initiative integrates LOS data, omnichannel communications, agent scripts, and borrower portal activity into a single interface, ensuring agents have a 360-degree view of the loan lifecycle and improving the speed and consistency of borrower support from application to closing.
CDL Salesforce MFD Workflow (Zendesk Migration) | CRM CDL, Zendesk | Implementation and Delivery | 50% | 10 |  |  | Enhancement | Backlog |  |  | Fulfillment & Operations Excellence | To provide a unified fulfillment environment for the Mortgage Success Team (MST) by migrating all core workflows from Zendesk to the enterprise CRM (LeadForce). This initiative integrates LOS data, omnichannel communications, agent scripts, and borrower portal activity into a single interface, ensuring agents have a 360-degree view of the loan lifecycle and improving the speed and consistency of borrower support from application to closing.
TrustPilot (Reputation Management) | SFMC | Planning and Design |  |  | 2026-02-15 | 2026-03-01 | Enhancement | In Progress |  |  | Omnichannel Engagement | To improve Pennymac’s online reputation and visibility in AI-driven and search-based discovery by increasing the volume and quality of Trustpilot reviews through a low-friction, login-free customer review experience. By integrating with Trustpilot’s API to generate encrypted, unique review URLs, this initiative enables customers to submit "Verified" reviews without account creation or 2FA, while passing dynamic loan context (Loan ID, Product Type, Loan Officer) to enable granular performance reporting and enhanced SEO visibility.
TrustPilot (Reputation Management) | SFMC | Implementation and Delivery | 30% | 3 |  |  | Enhancement | Backlog |  |  | Omnichannel Engagement | To improve Pennymac’s online reputation and visibility in AI-driven and search-based discovery by increasing the volume and quality of Trustpilot reviews through a low-friction, login-free customer review experience. By integrating with Trustpilot’s API to generate encrypted, unique review URLs, this initiative enables customers to submit "Verified" reviews without account creation or 2FA, while passing dynamic loan context (Loan ID, Product Type, Loan Officer) to enable granular performance reporting and enhanced SEO visibility.
SlashID Integration | CRM CDL, CRM TPO | Implementation and Delivery | 20% | 1 | 2026-03-15 | 2026-03-31 | Maintenance | Backlog |  |  | InfoSec, Risk & Compliance | To strengthen the enterprise cybersecurity framework by integrating SlashID with the primary CRM platform. This initiative enables automated, continuous monitoring of user identities, permission sets, and connected applications to identify over-privileged accounts and detect suspicious behavior in real-time. By centralizing security event analysis and tracking login patterns, the organization can proactively mitigate risks associated with weak MFA or shared accounts, ensuring a robust and compliant identity governance posture.
Zoom Interaction Summaries in CRM | CRM CDL | Planning and Design |  |  | 2026-03-01 | 2026-03-15 | Enhancement | Backlog |  |  | AI & Intelligent Automation | To enrich AI-generated Opportunity summaries within LeadForce by integrating Zoom call audio/transcripts and SMS communication history. This initiative ensures that CDL Loan Officers have a comprehensive, automated record of borrower interactions regardless of their working location (office or remote), eliminating manual note-taking, improving lead transition context, and leveraging AI to surface intent and key insights from diverse communication channels.
Zoom Interaction Summaries in CRM | CRM CDL | Implementation and Delivery | 30% | 2 |  |  | Enhancement | Backlog |  |  | AI & Intelligent Automation | To enrich AI-generated Opportunity summaries within LeadForce by integrating Zoom call audio/transcripts and SMS communication history. This initiative ensures that CDL Loan Officers have a comprehensive, automated record of borrower interactions regardless of their working location (office or remote), eliminating manual note-taking, improving lead transition context, and leveraging AI to surface intent and key insights from diverse communication channels.
CET - Non-QM Products | CRM CDL | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | Backlog |  |  | Strategic Growth & Channel Support | To diversify PennyMac’s loan portfolio by enabling Non-Qualified Mortgage (Non-QM) products within the Consumer Direct Lending (CDL) channel. This initiative involves updating Loan Officer (LO) workflows and borrower-facing digital portals to support Non-QM pricing, disclosures, and application paths, allowing the business to capture a broader market segment of non-traditional borrowers while maintaining automated compliance and data integrity throughout the sales cycle.
CET - Non-QM Products | CRM CDL | Implementation and Delivery | 20% | 2 |  |  | Enhancement | Backlog |  |  | Strategic Growth & Channel Support | To diversify PennyMac’s loan portfolio by enabling Non-Qualified Mortgage (Non-QM) products within the Consumer Direct Lending (CDL) channel. This initiative involves updating Loan Officer (LO) workflows and borrower-facing digital portals to support Non-QM pricing, disclosures, and application paths, allowing the business to capture a broader market segment of non-traditional borrowers while maintaining automated compliance and data integrity throughout the sales cycle.
TCPA Revocation Compliance | CRM CDL | Implementation and Delivery | 20% | 1 | 2026-03-13 | 2026-03-13 | Maintenance | Backlog |  |  | InfoSec, Risk & Compliance | To ensure strict adherence to updated FCC TCPA regulations regarding consent revocation. This initiative establishes a unified, enterprise-wide mechanism for processing customer opt-out requests across all communication channels, ensuring real-time preference updates and the delivery of mandatory confirmation messages to maintain legal compliance and protect the organization from litigation risks.
CDP Enhancements - CDP Non Port Activations | CRM CDL, SFMC | Implementation and Delivery | 20% | 2 | 2026-01-01 | 2026-01-30 | Enhancement | Done |  |  | Marketing Technology & Operations | To expand marketing reach by capturing unauthenticated (non-portal) web behavior through the Customer Data Platform (CDP). By identifying high-intent activity from anonymous site visitors and integrating this data with the communication delivery platform, this initiative enables the automated triggering of personalized follow-up campaigns, effectively re-engaging prospects and driving them toward the application funnel.
Horizon Enhancements - Sales | CRM CDL | Implementation and Delivery | 20% | 5 | 2026-03-13 | 2026-03-13 | Enhancement | Backlog |  |  | Platform Modernization & Legacy Sunset | To design and implement advanced sales workflows within the CRM platform to support the end-to-end migration of Loan Officer (LO) personas to the new cloud-native Loan Origination System (LOS). This initiative focuses on expanding lead management, automated status updates, and task-driven navigation to ensure high LO adoption and operational continuity as legacy systems are phased out.
Horizon Enhancements - SFMC | SFMC | Implementation and Delivery | 20% | 5 | 2026-03-13 | 2026-03-13 | Enhancement | Backlog |  |  | Platform Modernization & Legacy Sunset | To expand the capabilities of the enterprise marketing communication platform to support the unique journey requirements of the new cloud-native LOS. This initiative includes developing specialized transactional and marketing campaign templates for both Sales and Fulfillment (MFD) use cases, ensuring that borrower communications remain consistent, timely, and data-driven throughout the transition to the modern platform.
CRM - LO Visibility into Marketing | CRM CDL | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | Backlog |  |  | AI & Intelligent Automation | To empower Loan Officers with real-time visibility into the marketing ecosystem by implementing an AI-derived analysis of active solicitations and available offers within the CRM. This initiative enables LOs to have more informed, personalized conversations by understanding the exact offers a borrower has received, leading to higher conversion rates and a more cohesive customer experience across sales and marketing touchpoints.
CRM - LO Visibility into Marketing | CRM CDL | Implementation and Delivery | 30% | 3 |  |  | Enhancement | Backlog |  |  | AI & Intelligent Automation | To empower Loan Officers with real-time visibility into the marketing ecosystem by implementing an AI-derived analysis of active solicitations and available offers within the CRM. This initiative enables LOs to have more informed, personalized conversations by understanding the exact offers a borrower has received, leading to higher conversion rates and a more cohesive customer experience across sales and marketing touchpoints.
SFMC Lead Loading Improvements | SFMC | Implementation and Delivery | 20% | 1 | 2026-03-13 | 2026-03-13 | Maintenance | Backlog |  |  | Marketing Technology & Operations | To modernize the lead ingestion process for Salesforce Marketing Cloud (SFMC) by replacing the current manual SFTP and web-activation workflow with a standardized, automated data pipeline. By leveraging Snowflake and S3, this initiative eliminates the need for manual file uploads and custom URL activations, significantly reducing operational friction, minimizing the risk of ingestion errors, and accelerating the availability of leads for real-time marketing re-engagement.
Multitier Concession | CRM CDL | Planning and Design |  |  | 2026-03-13 | 2026-03-13 | Enhancement | Backlog |  |  | Fulfillment & Operations Excellence | To implement a structured, automated framework for requesting and managing Multitier Concessions, including Price Exceptions and Lender Credits, directly within the modern cloud-native platform. By integrating real-time loan data and the enterprise data model, this initiative provides Sales teams with faster support turnaround times and ensures that all pricing concessions are accurately tracked, governed, and reflected in downstream financial systems.
Multitier Concession | CRM CDL | Implementation and Delivery | 20% | 2 |  |  | Enhancement | Backlog |  |  | Fulfillment & Operations Excellence | To implement a structured, automated framework for requesting and managing Multitier Concessions, including Price Exceptions and Lender Credits, directly within the modern cloud-native platform. By integrating real-time loan data and the enterprise data model, this initiative provides Sales teams with faster support turnaround times and ensures that all pricing concessions are accurately tracked, governed, and reflected in downstream financial systems.
Horizon - Assumption Loans | CRM CDL, Zendesk, SFMC | Planning and Design |  |  | 2026-03-01 | 2026-03-15 | Enhancement |  |  |  | Platform Modernization & Legacy Sunset | To enable a seamless Assumption Loan lifecycle within Horizon, integrating LeadForce with Blend templates and Vesta data for self-serve application paths.
Horizon - Assumption Loans | CRM CDL, Zendesk, SFMC | Implementation and Delivery | 40% | 3 | 2026-03-15 | 2026-04-30 | Enhancement |  |  |  | Platform Modernization & Legacy Sunset | To enable a seamless Assumption Loan lifecycle within Horizon, integrating LeadForce with Blend templates and Vesta data for self-serve application paths.
Formulas:
Start Date = IF(ISBLANK([Initiative/Project]), "", TODAY())

## Initiative Descriptions
Initiative | Strategic Pillar | Succinct Business Objective (For Tracking Sheets) | Detailed Business Objective (For Slides) | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column 19 | Column 20 | Column 21 | Column 22
P3 Non-Del Core Notifications | Fulfillment & Operations Excellence | Modernize the P3 loan communication framework by centralizing transactional messaging within SFMC to eliminate legacy dependencies and improve data integrity. | To modernize the P3 loan communication framework by centralizing transactional messaging within Salesforce Marketing Cloud (SFMC). This initiative eliminates dependency on inflexible legacy systems, ensures data integrity through direct real-time queries, and empowers the business with full control over the branding and delivery logic of critical loan status updates.
NLVA (AI Virtual Agent) | AI & Intelligent Automation | Replace legacy IVR with AI-powered Natural Language Virtual Agents to improve routing accuracy, increase self-service, and expand Sales capacity. | To revolutionize PennyMac’s customer service framework by replacing traditional IVR systems with advanced Natural Language Virtual Agents (NLVA). By integrating AI-driven NLU and NLG capabilities, this project aims to eliminate call misrouting, unlock business capacity through automated initial outreach, and provide a seamless, human-like interaction experience for both inbound inquiries and outbound campaigns.
TPO Horizon Migration | Platform Modernization & Legacy Sunset | Migrate the Broker channel to a new, cloud-native Loan Origination System to improve performance, reduce technical debt, and streamline the loan lifecycle. | To transition the Broker Lending channel from its legacy Loan Origination System (LOS) to a modern, cloud-native platform. This migration aims to streamline the end-to-end loan lifecycle, enhance system performance, and provide a more intuitive interface for internal users and external partners, mirroring successful modernization efforts across other business units.
Customer Preference Management (CPM) | Marketing Technology & Operations | Implement a centralized preference center to allow granular "opt-down" controls, reducing blanket opt-outs and improving marketing contactability and compliance. | To implement a centralized, compliant platform that allows customers to fine-tune their communication preferences by specific marketing program types (e.g., Rate Alerts, General Marketing) and channels. By giving customers the choice to "opt-down" rather than completely out, Pennymac aims to preserve marketing opportunities, improve the customer experience, and ensure strict adherence to data privacy regulations.
CDP Personalization in CRM | AI & Intelligent Automation | Accelerate lead alert frequency from daily to hourly via CDP integration, enabling real-time prioritization and personalized sales engagement within Leadforce. | To enhance Sales productivity and speed-to-lead by integrating the Customer Data Platform (CDP) with Leadforce CRM. This initiative shifts Credco trigger alerts from daily to hourly delivery, empowering Loan Officers to prioritize high-intent opportunities faster while utilizing real-time behavioral attributes for highly personalized script delivery and borrower interactions.
TPO Contact Center | Strategic Growth & Channel Support | Implement an integrated Salesforce and Five9 solution with AI assistance for the TPO Call Center to streamline workflows and improve data-driven performance management. | To implement a fully integrated software solution for the TPO Account Executive (AE) Call Center, leveraging Salesforce as the primary CRM, Five9 for telephony, and an AI-powered assistant to help enhance AE productivity, streamline workflows, and improve data tracking for performance management.
Rapid Refi | Fulfillment & Operations Excellence | Automate lead creation from self-service applications to ensure immediate LO engagement and higher conversion for Rapid Refenance loans. | To bridge the gap between self-service applications and sales follow-up by automating lead generation from the consumer portal into the CRM. This ensures that every Rapid Refinance application is captured, assigned to a Loan Officer in real-time, and prioritized for engagement, thereby reducing drop-off rates and optimizing the sales funnel.
Borrower Self-Serve Scheduling | Omnichannel Engagement | Enable borrowers to self-schedule closing dates via integrated web tools, automating LOS updates and reducing manual MST agent follow-up. | To empower borrowers with a self-service closing scheduler accessible via digital communications. By enabling customers to select closing dates that automatically sync back to the Horizon LOS, this initiative improves the borrower experience while significantly reducing the manual coordination and follow-up workload for MST agents.
Horizon - MFD Enhancements | Fulfillment & Operations Excellence | Enhance Zendesk-LOS integration for MFD agents to streamline fulfillment workflows and provide proactive borrower support from submission to funding. | To transform the fulfillment experience by expanding Zendesk’s functional capabilities for MFD Agents supporting borrowers through the fulfillment process. By integrating Zendesk directly with the Horizon LOS, agents can manage end-to-end fulfillment steps within a single interface, eliminating "swivel-chair" workflows and ensuring borrowers receive seamless, proactive support from loan submission through to funding.
Attack Surface Management (ASM) | InfoSec, Risk & Compliance | Establish a continuous remediation framework for InfoSec findings to proactively address system vulnerabilities and ensure organizational compliance. | To strengthen Pennymac’s cybersecurity posture by implementing a systematic process for remediating Attack Surface Management (ASM) findings. This initiative empowers division owners to proactively reconcile vulnerabilities—including End-of-Life systems, misconfigurations, and web-based threats (XSS, Injection)—ensuring continuous patching and protection against zero-day exploits while safeguarding sensitive data.
Pennymac Data Model (PDM) for Servicing | Enterprise Data Strategy | Standardize downstream data consumption from the new servicing platform using the Pennymac Data Model (PDM) to ensure consistency and streamlined integration. | To implement the Pennymac Data Model (PDM) as the enterprise-wide standard for all downstream data consumption originating from the new servicing platform. By aligning servicing data with the universal PDM schema, this initiative ensures data consistency across business units, simplifies reporting and analytics, and accelerates the integration of servicing data with other core enterprise systems.
PDM for TPO Horizon | Enterprise Data Strategy | Map TPO data fields to the PDM standard to ensure seamless integration with the new LOS and enable governed, standardized data consumption. | To design, model, and implement the PDM data standard for the TPO production channel as it migrates to the new Loan Origination System (LOS). By creating a single, governed source of truth that publishes updates in PDM format, this initiative enables standardized downstream consumption across all integrated systems and facilitates the decommissioning of legacy data interfaces.
CDL Legacy Platform Sunset | Platform Modernization & Legacy Sunset | Decommission the legacy Loan Origination System (LOS) and associated integrations to reduce maintenance costs and finalize the transition to the modern platform. | To formally decommission and sunset the legacy Loan Origination System (LOS) and its supporting infrastructure following the successful migration to the modern production platform. This initiative includes the retirement of legacy integrations and the archival of historical data, ultimately reducing operational overhead, eliminating technical debt, and mitigating risks associated with maintaining outdated systems.
FTC Data Disposal | Cybersecurity, Risk & Compliance | Implement a systematic data disposal framework for inactive customer NPPI to ensure compliance with the FTC Safeguard Rule and minimize data privacy risks. | To establish a comprehensive enterprise-wide framework for the secure disposal of Non-Public Personal Information (NPPI) in accordance with the FTC Safeguard Rule. This initiative involves the systematic identification, archival, and deletion or anonymization of inactive customer data across internal applications, vendor platforms, and decommissioned systems to ensure federal compliance and protect consumer privacy.
Communication Platform: Power+ Chat Strategy | Omnichannel Engagement | Migrate TPO client-facing groups to a unified communication platform to enable Voice, SMS, and Chat capabilities, replacing email-based workflows with real-time, intelligent routing. | To modernize communication within the TPO channel by migrating Client Management, Closing, and Underwriting teams to a unified omnichannel platform. This initiative integrates Voice, SMS, and Chat capabilities directly into the partner and settlement agent portals, replacing inefficient email-based workflows with real-time collaboration and intelligent routing to ensure partners are connected to specialists instantly.
Salesforce as System of Record & Client Approval | Platform Modernization & Legacy Sunset | Establish the CRM as the authoritative SOR for client data and approvals, unifying data standards and automating synchronization with the LOS and downstream systems. | To transition client/partner administrative data and the end-to-end approval lifecycle to a centralized CRM platform as the primary System of Record (SOR). This initiative unifies sales, service, and onboarding interactions into a single 360-degree view, enforcing data validation and automated synchronization with the Loan Origination System (LOS) and other downstream systems. By automating the push of approved profiles and metadata, the organization ensures a single version of truth, improves data quality, and eliminates manual entry and redundant workflows across the enterprise.
Sub-servicing Client Request Management Tool | Strategic Growth & Channel Support | Replace manual tracking with an automated, integrated client request management system to support subservicing business growth and improve resolution efficiency. | To modernize the subservicing client support framework by replacing manual tracking processes with an integrated, automated request management system. This initiative leverages a scalable support platform to centralize ticket submissions via the client portal, implement intelligent routing and SLA tracking, and provide real-time status visibility for both internal teams and subservicing clients, ensuring the operational capacity required for significant portfolio growth.
Post-Closing Items Tracking | Fulfillment & Operations Excellence | Migrate TPO and CDL post-closing tracking from manual sheets to a structured workflow system to enable automated SLA management and regulatory reporting. | To modernize the management of post-closing tasks by implementing a structured workflow environment for TPO and CDL production. By moving from manual spreadsheets to a categorized system—covering Collateral, Servicing Updates, and Production Support—this initiative enables automated SLA tracking and robust reporting, ensuring timely remediation of loan-level items and strict adherence to regulatory compliance standards.
Deprecate Kirby | Enterprise Data Strategy | Replace legacy data ingestion tools with modern infrastructure to remove dependencies and enhance CET data pipeline functionality. | To modernize the data ecosystem by deprecating the legacy Kirby ingestion tool in favor of robust, scalable data landing infrastructure for the CET team. This initiative creates standardized ingestion patterns that eliminate technical dependencies, improve pipeline reliability, and introduce advanced functionality to accelerate data delivery for critical business operations.
SFMC Pipeline Deployment Automation | Marketing Technology & Operations | Implement an automated deployment tool for Salesforce Marketing Cloud to replace manual release processes, ensuring consistent migrations and faster speed-to-market. | To implement a robust CI/CD pipeline for Salesforce Marketing Cloud (SFMC) by selecting and integrating a specialized deployment automation tool. This initiative aims to replace high-risk manual deployment processes with automated version control and migration workflows, significantly reducing environment inconsistencies, minimizing release-related errors, and accelerating the delivery of marketing campaigns and transactional communications.
New Zendesk Group - Service Orders | Fulfillment & Operations Excellence | Transition the Service Orders team from a manual shared inbox to a structured Zendesk environment to improve ticket prioritization and tracking across multiple task types. | To enhance operational efficiency for the Service Orders team by migrating workflow management from a shared email inbox to a dedicated Zendesk group. This initiative enables the structured labeling and prioritization of diverse task types—including appraisal/AVM delivery, flood certifications, fraud alerts, and dispositions—providing visibility into volumes and ensuring faster, more accurate processing of critical loan-level service orders.
Scowtt (Predictive Modeling Integration) | AI & Intelligent Automation | Automate the data pipeline between the CRM and the predictive modeling platform to enable AI-driven propensity scoring for targeted marketing. | To establish a secure and automated data integration between the CRM (LeadForce) and the Scowtt predictive modeling platform. This initiative involves mapping core CRM objects, configuring secure access through Field-Level Security (FLS), and ensuring a robust data sync to support AI-driven propensity scoring, ultimately empowering the marketing team with high-accuracy pilot data for targeted customer engagement.
Acquia Digital Asset Management (DAM) | Marketing Technology & Operations | Centralize marketing assets within a unified digital asset management platform to streamline content creation and ensure brand consistency across communication channels. | To implement an enterprise-grade Digital Asset Management (DAM) solution integrated with the marketing communication platform. This initiative centralizes all digital assets—images, videos, and templates—providing a single source of truth for marketing teams. By automating asset availability within the delivery tools, the organization reduces manual upload times, ensures global brand consistency, and improves speed-to-market for multi-channel campaigns.
MST LeadForce Migration | Fulfillment & Operations Excellence | Migrate MST fulfillment workflows from Zendesk to the CRM to centralize borrower interactions and eliminate cross-platform "swivel-chair" activity. | To provide a unified fulfillment environment for the Mortgage Success Team (MST) by migrating all core workflows from Zendesk to the enterprise CRM (LeadForce). This initiative integrates LOS data, omnichannel communications, agent scripts, and borrower portal activity into a single interface, ensuring agents have a 360-degree view of the loan lifecycle and improving the speed and consistency of borrower support from application to closing.
TrustPilot (Reputation Management) | Omnichannel Engagement | Implement a low-friction Trustpilot API integration to capture verified customer reviews and boost search visibility without login barriers. | To improve Pennymac’s online reputation and visibility in AI-driven and search-based discovery by increasing the volume and quality of Trustpilot reviews through a low-friction, login-free customer review experience. By integrating with Trustpilot’s API to generate encrypted, unique review URLs, this initiative enables customers to submit "Verified" reviews without account creation or 2FA, while passing dynamic loan context (Loan ID, Product Type, Loan Officer) to enable granular performance reporting and enhanced SEO visibility.
SlashID Integration (CRM Security) | Cybersecurity, Risk & Compliance | Integrate SlashID with the CRM platform to monitor user identities, permissions, and security events, ensuring proactive protection against identity-based risks. | To strengthen the enterprise cybersecurity framework by integrating SlashID with the primary CRM platform. This initiative enables automated, continuous monitoring of user identities, permission sets, and connected applications to identify over-privileged accounts and detect suspicious behavior in real-time. By centralizing security event analysis and tracking login patterns, the organization can proactively mitigate risks associated with weak MFA or shared accounts, ensuring a robust and compliant identity governance posture.
Zoom & SMS Integration for AI Summaries | AI & Intelligent Automation | Integrate Zoom call transcripts and SMS history into Salesforce AI summaries to provide CDL Loan officers with automated, multi-channel interaction context. | To enrich AI-generated Opportunity summaries within LeadForce by integrating Zoom call audio/transcripts and SMS communication history. This initiative ensures that CDL Loan Officers have a comprehensive, automated record of borrower interactions regardless of their working location (office or remote), eliminating manual note-taking, improving lead transition context, and leveraging AI to surface intent and key insights from diverse communication channels.
Non-QM Product Integration | Strategic Growth & Channel Support | Expand the CDL channel's offerings by integrating Non-Qualified Mortgage (Non-QM) products into the LO and borrower digital journeys. | To diversify PennyMac’s loan portfolio by enabling Non-Qualified Mortgage (Non-QM) products within the Consumer Direct Lending (CDL) channel. This initiative involves updating Loan Officer (LO) workflows and borrower-facing digital portals to support Non-QM pricing, disclosures, and application paths, allowing the business to capture a broader market segment of non-traditional borrowers while maintaining automated compliance and data integrity throughout the sales cycle.
TCPA Revocation Compliance | Cybersecurity, Risk & Compliance | Implement enterprise-wide opt-out processing and confirmation messaging to meet new FCC TCPA revocation standards by April 2026. | To ensure strict adherence to updated FCC TCPA regulations regarding consent revocation. This initiative establishes a unified, enterprise-wide mechanism for processing customer opt-out requests across all communication channels, ensuring real-time preference updates and the delivery of mandatory confirmation messages to maintain legal compliance and protect the organization from litigation risks.
CDP Enhancements - Non-Port Activations | Marketing Technology & Operations | Capture unauthenticated web activity via the CDP and trigger automated follow-up marketing campaigns to increase top-of-funnel lead conversion. | To expand marketing reach by capturing unauthenticated (non-portal) web behavior through the Customer Data Platform (CDP). By identifying high-intent activity from anonymous site visitors and integrating this data with the communication delivery platform, this initiative enables the automated triggering of personalized follow-up campaigns, effectively re-engaging prospects and driving them toward the application funnel.
CDL Horizon CRM Workflow Enhancements | Platform Modernization & Legacy Sunset | Implement CRM workflow enhancements to support the transition of Sales and Loan Officer personas to the new cloud-native LOS environment. | To design and implement advanced sales workflows within the CRM platform to support the end-to-end migration of Loan Officer (LO) personas to the new cloud-native Loan Origination System (LOS). This initiative focuses on expanding lead management, automated status updates, and task-driven navigation to ensure high LO adoption and operational continuity as legacy systems are phased out.
CDL Horizon Marketing Enhancements | Platform Modernization & Legacy Sunset | Expand communication platform capabilities to support specialized Sales and Fulfillment (MFD) journeys on the new cloud-native LOS. | To expand the capabilities of the enterprise marketing communication platform to support the unique journey requirements of the new cloud-native LOS. This initiative includes developing specialized transactional and marketing campaign templates for both Sales and Fulfillment (MFD) use cases, ensuring that borrower communications remain consistent, timely, and data-driven throughout the transition to the modern platform.
CRM - LO Visibility into Marketing | AI & Intelligent Automation | Implement an AI-derived analysis of active solicitations and available offers within the CRM to give Loan Officers real-time visibility into borrower-facing marketing. | To empower Loan Officers with real-time visibility into the marketing ecosystem by implementing an AI-derived analysis of active solicitations and available offers within the CRM. This initiative enables LOs to have more informed, personalized conversations by understanding the exact offers a borrower has received, leading to higher conversion rates and a more cohesive customer experience across sales and marketing touchpoints.
SFMC Lead Loading Improvements | Marketing Technology & Operations | Standardize and automate SFMC lead ingestion using Snowflake and S3 to eliminate manual SFTP uploads and custom URL activations. | To modernize the lead ingestion process for Salesforce Marketing Cloud (SFMC) by replacing the current manual SFTP and web-activation workflow with a standardized, automated data pipeline. By leveraging Snowflake and S3, this initiative eliminates the need for manual file uploads and custom URL activations, significantly reducing operational friction, minimizing the risk of ingestion errors, and accelerating the availability of leads for real-time marketing re-engagement.
Multitier Concession (Price Exceptions) | Fulfillment & Operations Excellence | Enable automated requests for Price Exceptions and Lender Credits within the modern LOS to streamline sales support and data integration. | To implement a structured, automated framework for requesting and managing Multitier Concessions, including Price Exceptions and Lender Credits, directly within the modern cloud-native platform. By integrating real-time loan data and the enterprise data model, this initiative provides Sales teams with faster support turnaround times and ensures that all pricing concessions are accurately tracked, governed, and reflected in downstream financial systems.
Horizon - Assumption Loans | Platform Modernization & Legacy Sunset | Implement LeadForce and Zendesk workflows to support Assumption Loan processing. | To enable a seamless Assumption Loan lifecycle within Horizon, integrating LeadForce with Blend templates and Vesta data for self-serve application paths.

## Strategic Themes
Strategic Pillar | Initiatives Included | Pillar Objective | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column 19 | Column 20 | Column 21 | Column 22 | Column 23
AI & Intelligent Automation | NLVA, CDP CRM Alerts, Scowtt Integration, Zoom/SMS AI Summaries, LO Visibility into Marketing | Leverage AI and machine learning to automate complex decisioning, enhance sales intelligence, and revolutionize customer interactions.
Platform Modernization & Legacy Sunset | TPO Horizon Migration, CDL Legacy Platform Sunset, CDL Horizon CRM Workflow Enhancements, CDL Horizon Marketing Enhancements, Salesforce as System of Record, Horizon - Assumption Loans | Retire high-maintenance legacy debt and transition all production channels to a unified, cloud-native architecture.
Enterprise Data Strategy | PDM for Servicing, PDM for TPO Horizon, Deprecate Kirby | Establish a single, governed source of truth across the enterprise using a standardized data model (PDM) and centralized SOR.
InfoSec, Risk & Compliance | Attack Surface Management (ASM), FTC Data Disposal, TCPA Revocation Compliance, SlashID Integration | Proactively mitigate technical vulnerabilities, ensure strict adherence to federal regulations, and protect customer identity and data privacy.
Omnichannel Engagement | Communication Platform (Power+ Chat), Borrower Self-Serve Scheduling, TrustPilot Integration | Modernize the borrower and partner experience by providing low-friction, real-time communication and self-service capabilities.
Fulfillment & Operations Excellence | P3 Non-Del Core Notifications, Horizon MFD Enhancements, New Zendesk Service Orders, MST LeadForce Migration, Post-Closing Items Tracking, Multitier Concessions, Rapid Refi | Eliminate manual "swivel-chair" activity by consolidating fulfillment workflows into a structured, automated environment.
Marketing Technology & Operations | SFMC Pipeline Automation, SFMC Lead Loading Improvements, CDP Non-Port Behavioral Activations, Acquia DAM, Customer Preference Management (CPM) | Optimize the speed and reliability of marketing deployments through DevOps maturity and automated data ingestion patterns.
Strategic Growth & Channel Support | Sub-servicing Client Request Management, Non-QM Product Integration, TPO Contact Center (Salesforce/Five9) | Build the operational capacity and product diversity required to support significant volume growth in specialized and emerging channels.