## Data
Initiative Name | Old Initiative Name | Team(s) | Phase | Start Quarter 2026 | End Quarter 2026 | Theme | Business Sponsor
Pennymac Data Model (PDM) - Servicing |  | Dragon | Planning and Design | 2026-01-01 | 2026-04-30 | Critical/Compliance-Reputational Risk Mitigation | Enterprise Data
Pennymac Data Model (PDM) - Servicing |  | Dragon | Implementation and Delivery | 2026-04-01 | 2026-09-30 | Critical/Compliance-Reputational Risk Mitigation | Enterprise Data
MBO Data Management Work |  | Customers Falcon | Planning and Design | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Enterprise Data
MBO Data Management Work |  | Customers Falcon | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Enterprise Data
Pennymac SOC2 Type 2 FreddieMac requirement |  | Customers Falcon, Kestrel | Planning and Design | 2026-04-01 | 2026-09-30 | Critical/Compliance-Reputational Risk Mitigation | Info Sec
Pennymac SOC2 Type 2 FreddieMac requirement |  | Customers Falcon, Kestrel | Implementation and Delivery | 2026-07-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Info Sec
Attack Surface Management (ASM) |  | Customers Falcon, Kestrel | Planning and Design | 2026-01-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Info Sec
Attack Surface Management (ASM) |  | Customers Falcon, Kestrel | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Info Sec
CPM - Customer Preference Management |  | Customers Raptor | Planning and Design | 2026-01-01 | 2026-03-31 | Custmer Self Service | Marketing
CPM - Customer Preference Management |  | Customers Raptor | Implementation and Delivery | 2026-01-01 | 2026-03-31 | Custmer Self Service | Marketing
DCX - Chat/Bot for Sales/Marketing |  | Kestrel | Planning and Design | 2026-07-01 | 2026-12-31 | Custmer Self Service | Marketing
DCX - Chat/Bot for Sales/Marketing |  | Kestrel | Implementation and Delivery | 2026-07-01 | 2026-12-31 | Custmer Self Service | Marketing
Credit Monitoring (Experian) |  | Customers Raptor | Planning and Design | 2026-03-18 | 2026-03-27 | Digital Exp/Personalization | Marketing
Credit Monitoring (Experian) |  | Customers Raptor | Implementation and Delivery | 2026-04-08 | 2026-05-06 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Dashboard P1 |  | Customers Raptor | Planning and Design | 2026-01-01 | 2026-01-20 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Dashboard P1 |  | Customers Raptor | Implementation and Delivery | 2026-01-21 | 2026-04-08 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Dashboard P2 |  | Customers Raptor | Planning and Design | 2026-03-18 | 2026-04-01 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Dashboard P2 |  | Customers Raptor | Implementation and Delivery | 2026-04-01 | 2026-09-30 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Loan Summary Pg |  | Customers Raptor | Planning and Design | 2026-06-24 | 2026-07-21 | Digital Exp/Personalization | Marketing
Marketing UI Changes-Loan Summary Pg |  | Customers Raptor | Implementation and Delivery | 2026-07-22 | 2026-11-11 | Digital Exp/Personalization | Marketing
Mobile/Digital Channels Analytics Dashboard |  | Customers Falcon | Planning and Design | 2026-04-15 | 2026-05-12 | Marketing Enhancements | Marketing
Mobile/Digital Channels Analytics Dashboard |  | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-09-30 | Marketing Enhancements | Marketing
CDL Sales/Marketing Small Enhancements |  | Kestrel | Planning and Design | 2026-01-01 | 2026-12-31 | Marketing Enhancements | Marketing
CDL Sales/Marketing Small Enhancements |  | Kestrel | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Marketing Enhancements | Marketing
Acquia DAM |  | Kestrel | Planning and Design | 2026-10-01 | 2026-12-31 | Marketing Enhancements | Marketing
Acquia DAM |  | Kestrel | Implementation and Delivery | 2026-10-01 | 2026-12-31 | Marketing Enhancements | Marketing
HELOC |  | Customers Falcon | Planning and Design | 2026-07-01 | 2026-12-31 | Custmer Self Service | Plaisse
HELOC |  | Customers Falcon | Implementation and Delivery | 2026-07-01 | 2026-12-31 | Custmer Self Service | Plaisse
SSE Internal and External Interfaces |  | Dragon | Planning and Design | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Plaisse
SSE Internal and External Interfaces |  | Dragon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Plaisse
SSE Non-Centric Field Remediation (Servicing SaaS Platform) |  | Customers Falcon | Planning and Design | 2026-01-01 | 2026-03-31 | Servicing Commercialization | Plaisse
SSE Non-Centric Field Remediation (Servicing SaaS Platform) |  | Customers Falcon | Implementation and Delivery | 2026-01-01 | 2026-03-31 | Servicing Commercialization | Plaisse
Auth0 Integration (Servicing SaaS Platform) |  | Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Servicing Commercialization | Plaisse
Auth0 Integration (Servicing SaaS Platform) |  | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Servicing Commercialization | Plaisse
Servicing Small Enhancements |  | Customers Falcon, Customers Raptor, Kestrel | Planning and Design | 2026-01-01 | 2026-12-31 | Servicing Enhancements | Servicing
Servicing Small Enhancements |  | Customers Falcon, Customers Raptor, Kestrel | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Servicing Enhancements | Servicing
Subservicing Single Sign On |  | Dragon | Planning and Design | 2026-01-01 | 2026-06-30 | Servicing Enhancements | Servicing
Subservicing Single Sign On |  | Dragon | Implementation and Delivery | 2026-01-01 | 2026-06-30 | Servicing Enhancements | Servicing
AI Repo Readiness | AI Repo Readiness | Kestrel, Customers Falcon | Planning and Design | 2026-01-01 | 2026-03-31 | Customer Transaction Optimization | Tech
AI Repo Readiness | AI Repo Readiness | Kestrel, Customers Falcon | Implementation and Delivery | 2026-01-01 | 2026-03-31 | Customer Transaction Optimization | Tech
Application Stability and Resilience |  | Kestrel | Planning and Design | 2026-04-01 | 2026-06-30 | Customer Transaction Optimization | Tech
Application Stability and Resilience |  | Kestrel | Implementation and Delivery | 2026-04-01 | 2026-06-30 | Customer Transaction Optimization | Tech
Testing and Build Infrastructure |  | Customers Falcon, Customers Raptor | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Testing and Build Infrastructure |  | Customers Falcon, Customers Raptor | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Customers Identity Modernization Program | Replace IDS with Auth0 | Dragon, Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Tech
Customers Identity Modernization Program | Replace IDS with Auth0 | Dragon, Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Tech
Infrastructure Efficiency & Velocity | DCX - Tech - OnePipeline - Migrate Azure DevOps Repos to OnePipeline | Customers Falcon | Planning and Design | 2026-04-01 | 2026-06-30 | Critical/Compliance-Reputational Risk Mitigation | Tech
Infrastructure Efficiency & Velocity | DCX - Tech - OnePipeline - Migrate Azure DevOps Repos to OnePipeline | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-06-30 | Critical/Compliance-Reputational Risk Mitigation | Tech
Configuration (In Application Feature Flags and Pennymac Reference Removal)* (Servicing SaaS Platform) |  | Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Tech
Configuration (In Application Feature Flags and Pennymac Reference Removal)* (Servicing SaaS Platform) |  | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Critical/Compliance-Reputational Risk Mitigation | Tech
DevOps Standardization & Delivery Acceleration | DCX - Tech - Migration - GitLab Repos to OnePipeline | Kestrel | Planning and Design | 2026-04-01 | 2026-06-30 | Customer Transaction Optimization | Tech
DevOps Standardization & Delivery Acceleration | DCX - Tech - Migration - GitLab Repos to OnePipeline | Kestrel | Implementation and Delivery | 2026-04-01 | 2026-06-30 | Customer Transaction Optimization | Tech
Servicing Maintenance |  | Customers Falcon, Customers Raptor | Planning and Design | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Servicing Maintenance |  | Customers Falcon, Customers Raptor | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Transaction Experience Optimization | Deferred Maintenance - SSE Payment Handshake Optimization | Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Transaction Experience Optimization | Deferred Maintenance - SSE Payment Handshake Optimization | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
DCX - Tech - Deferred Maintenance - Remove Unused Code, Content, and Toggles | DCX - Tech - Deferred Maintenance - Remove Unused Code, Content, and Toggles | Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
DCX - Tech - Deferred Maintenance - Remove Unused Code, Content, and Toggles | DCX - Tech - Deferred Maintenance - Remove Unused Code, Content, and Toggles | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Cloud Efficiency & Performance Optimization | DCX - Tech - Migration - Legacy Stacks to Serverless | Customers Falcon | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Cloud Efficiency & Performance Optimization | DCX - Tech - Migration - Legacy Stacks to Serverless | Customers Falcon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Operational Stability & Resilience | DCX - Tech - EOL Maintenance | Customers Falcon | Planning and Design | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Operational Stability & Resilience | DCX - Tech - EOL Maintenance | Customers Falcon | Implementation and Delivery | 2026-01-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Unified Test Reporting / Test Automation |  | Customers Falcon, Customers Raptor, Kestrel, Dragon | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Unified Test Reporting / Test Automation |  | Customers Falcon, Customers Raptor, Kestrel, Dragon | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
DCX - Tech - Deferred Maintenance - PennyHome New Relic Error Remediation | DCX - Tech - Deferred Maintenance - PennyHome New Relic Error Remediation | Customers Falcon, Customers Raptor, Kestrel | Planning and Design | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
DCX - Tech - Deferred Maintenance - PennyHome New Relic Error Remediation | DCX - Tech - Deferred Maintenance - PennyHome New Relic Error Remediation | Customers Falcon, Customers Raptor, Kestrel | Implementation and Delivery | 2026-04-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Agile Infrastructure Scaling | Database Virtualization | Customers Falcon, Dragon | Planning and Design | 2026-07-01 | 2026-09-30 | Customer Transaction Optimization | Tech
Agile Infrastructure Scaling | Database Virtualization | Customers Falcon, Dragon | Implementation and Delivery | 2026-07-01 | 2026-09-30 | Customer Transaction Optimization | Tech
Nutanix Migration (Instant Clones) |  | Dragon | Planning and Design | 2026-07-01 | 2026-12-31 | Customer Transaction Optimization | Tech
Nutanix Migration (Instant Clones) |  | Dragon | Implementation and Delivery | 2026-07-01 | 2026-12-31 | Customer Transaction Optimization | Tech
DCX 2026.1 |  |  | Release | 2026-01-01 | 2026-01-07
DCX 2026.2 |  |  | Release | 2026-01-07 | 2026-01-27
DCX 2026.2.1 |  |  | Release | 2026-01-27 | 2026-02-19
DCX 2026.2.2 |  |  | Release | 2026-02-19 | 2026-03-03
DCX 2026.3 |  |  | Release | 2026-03-03 | 2026-03-08
DCX 2026.4 |  |  | Release | 2026-03-08 | 2026-03-17
DCX 2026.5 |  |  | Release | 2026-03-17 | 2026-03-25
DCX 2026.6 |  |  | Release | 2026-03-25 | 2026-04-08

## Deck
Notebook
https://docs.google.com/presentation/d/1wmKf93hzXXvsttpSM42klKQDjfa2azGys-qLxYyUJBo/edit?usp=sharing
Roadmap
https://docs.google.com/presentation/d/1iT1HKWEAtIvw2e7SDJ7c7c69313VJICeT8yTeWmpYMI/edit?usp=sharing